Production Documentation

وثائق الإنتاج — قوائم وجداول ومراجعات الجودة

# Master Shot List  —  قائمة اللقطات الرئيسية

| # | Act | Title (EN) | Dur | Movement | Transition Out |
| --- | --- | --- | --- | --- | --- |
| 1 | 1 | The Kingdom of Saudi Arabia | 6s | Push-in | Fade |
| 2 | 1 | Natural Wealth | 5s | Pull-back | Fade |
| 3 | 1 | Vision 2030 | 5s | Left drift | Slide |
| 4 | 1 | Environmental Capital | 5s | Right drift | Fade |
| 5 | 1 | The Living Desert | 5s | Push-in | Fade |
| 6 | 1 | Sarawat Mountains | 5s | Pull-back | Slide |
| 7 | 1 | Mangrove Forests | 5s | Left drift | Fade |
| 8 | 1 | A Legacy for Generations | 6s | Right drift | Fade |
| 9 | 2 | Environmental Challenges | 5s | Push-in | Slide |
| 10 | 2 | Water Scarcity | 5s | Pull-back | Fade |
| 11 | 2 | Data is Power | 5s | Left drift | Fade |
| 12 | 2 | Environmental Intelligence | 5s | Right drift | Slide |
| 13 | 2 | The National Platform | 5s | Push-in | Fade |
| 14 | 2 | Artificial Intelligence | 5s | Pull-back | Fade |
| 15 | 2 | Digital Transformation | 5s | Left drift | Slide |
| 16 | 2 | From Challenge to Opportunity | 5s | Right drift | Fade |
| 17 | 3 | National Environmental Assets Registry | 6s | Push-in | Fade |
| 18 | 3 | Geographic Information Systems | 5s | Pull-back | Slide |
| 19 | 3 | Satellites | 6s | Left drift | Fade |
| 20 | 3 | The Digital Twin | 6s | Right drift | Fade |
| 21 | 3 | Continuous Monitoring | 5s | Push-in | Slide |
| 22 | 3 | Environmental Governance | 5s | Pull-back | Fade |
| 23 | 3 | Cybersecurity | 5s | Left drift | Fade |
| 24 | 3 | Decision Support | 5s | Right drift | Slide |
| 25 | 4 | Investing in Nature | 6s | Push-in | Fade |
| 26 | 4 | Environmental Markets | 5s | Pull-back | Fade |
| 27 | 4 | Natural Capital | 5s | Left drift | Slide |
| 28 | 4 | Biodiversity | 5s | Right drift | Fade |
| 29 | 4 | Water | 5s | Push-in | Fade |
| 30 | 4 | Forests | 5s | Pull-back | Slide |
| 31 | 4 | Protected Areas | 5s | Left drift | Fade |
| 32 | 4 | Smart Cities | 5s | Right drift | Fade |
| 33 | 4 | National Intelligence | 5s | Push-in | Slide |
| 34 | 5 | A Future We Build | 5s | Pull-back | Fade |
| 35 | 5 | Global Leadership | 5s | Left drift | Fade |
| 36 | 5 | International Standing | 5s | Right drift | Slide |
| 37 | 5 | Vision 2030 | 5s | Push-in | Fade |
| 38 | 5 | National Prosperity | 5s | Pull-back | Fade |
| 39 | 5 | From Earth to Sky | 6s | Left drift | Slide |
| 40 | 5 | National Environmental Assets Economy Platform | 7s | Right drift | — |

# Production Schedule  —  جدول الإنتاج

| Day 1 — Pre-production | Approve storyboard, color palette, voice-over talent selection (Ar + En). |
| --- | --- |
| Day 2 — Asset generation | Generate/curate all 40 hero images. QC pass. Approve final set. |
| Day 3 — Motion assembly | Assemble Remotion scenes, Ken Burns tuning, transitions. |
| Day 4 — Voice-over recording | Record Ar + En VO. Rough sync. Approve reads. |
| Day 5 — Sound design & music | Ambient bed, foley, music score, final mix. |
| Day 6 — Final grade & render | Color pass, subtitles, final MP4 masters (4K/1080p). |
| Day 7 — Delivery review | Executive review, revisions, final approval. |

# Asset List  —  قائمة الأصول

| Hero images | 40 × 16:9 PNG, ~1.5–2.1 MB each, saved as scene-01.png … scene-40.png. |
| --- | --- |
| Fonts | Tajawal (Arabic), Playfair Display (Latin serif), Inter (Latin sans). |
| Sadu pattern | Procedural CSS gradient — no external asset. |
| Brand mark | Small rotated square + wordmark — inline SVG/CSS. |
| Music | Original score to be commissioned (see Music Direction). |
| Voice-over | Ar (formal male + female alt), En (neutral international). |
| Deliverables | national-environmental-documentary.mp4 · Storyboard.docx · Production-Bible.docx · Production-Docs.docx |

# Image Tracking Sheet  —  ورقة تتبع الصور

| # | File | Status | QC | Notes |
| --- | --- | --- | --- | --- |
| 1 | scene-01.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 2 | scene-02.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 3 | scene-03.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 4 | scene-04.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 5 | scene-05.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 6 | scene-06.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 7 | scene-07.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 8 | scene-08.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 9 | scene-09.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 10 | scene-10.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 11 | scene-11.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 12 | scene-12.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 13 | scene-13.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 14 | scene-14.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 15 | scene-15.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 16 | scene-16.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 17 | scene-17.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 18 | scene-18.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 19 | scene-19.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 20 | scene-20.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 21 | scene-21.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 22 | scene-22.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 23 | scene-23.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 24 | scene-24.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 25 | scene-25.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 26 | scene-26.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 27 | scene-27.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 28 | scene-28.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 29 | scene-29.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 30 | scene-30.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 31 | scene-31.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 32 | scene-32.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 33 | scene-33.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 34 | scene-34.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 35 | scene-35.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 36 | scene-36.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 37 | scene-37.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 38 | scene-38.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 39 | scene-39.png | Generated | Pass | 16:9 · Cinematic · No text/logos |
| 40 | scene-40.png | Generated | Pass | 16:9 · Cinematic · No text/logos |

# Rendering Checklist  —  قائمة التصيير

| Codec | H.264 · MP4 |
| --- | --- |
| Resolution | 1920 × 1080 · 30 fps |
| Duration | ~209s of content (before transition overlap adjustments) |
| Audio | Muted in current build — VO/music to be laid in post |
| Concurrency | 2 (sandbox safe) |

# Quality Control Checklist  —  قائمة ضبط الجودة

| Consistency | Same color grade across all 40 shots — approved. |
| --- | --- |
| Typography | Arabic (Tajawal) + Latin (Playfair + Inter) rendering correctly. |
| No forbidden content | No text/logos in generated imagery. |
| Bilingual | Every scene shows Ar + En title + sub. |
| Motion | No robotic linear motion; springs on entrances. |
| Transitions | Fade + slide alternating rhythm. |

# Final Review Checklist  —  المراجعة النهائية

| Executive review | Present to executive committee for approval. |
| --- | --- |
| Cultural review | Confirm Arabic phrasing and cultural tone. |
| Legal review | Confirm no misuse of national symbols or unverifiable claims. |
| Delivery formats | 1080p master · 4K uprez (post) · 30s promo cutdown · 6s teaser. |